## Sheet1
Typical Two Week Sprint Timeline
Day 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Facilitator | Team Event/Session |  |  | Time Needed |  | Frequency in Sprint |  | Preferred Day in Sprint
Scrum Master | Backlog Refinement |  |  | 1-2 hours |  | 2 times a sprint (once a week) in the beginning. It can be reduced to once a sprint when there are 2-3 sprints worth of ready-to-sprint work. |  | Day 3, or 4, or 5, or 6, or 7
Service Manager | Stakeholder Prioritization |  |  | Length determined by the extent of the conversation. Can be as little as 10 minutes as long as an hour. |  | Once in a sprint |  | Day 3, or 4, or 5, or 6, or 7
Scrum Master | Sprint Review Planning |  |  | 10-15 minutes |  | Once in a sprint |  | Day 9
Scrum Master | Sprint Review/Demo |  |  | Length determined by the number of features demoed. Can be as little as 10 minutes as long as an hour |  | Once in a sprint |  | Day 10
Scrum Master | Sprint Retrospective |  |  | 1-2 hours |  | Once in a sprint |  | Day 10 is the best, but this could be done at the beginning of Day 1 followed by planning.
Scrum Master | Sprint Planning |  |  | 1-4 hours |  | Once in a sprint |  | Day 10 or 1
NOTES: | Review, Retro and Planning events are run in this order so that teams have a chance to mentally close out the sprint before embarking upon the next one.