## Sprint 9
PMO Team
| Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Sprint | %
| 2016-05-16 | 2016-05-17 | 2016-05-18 | 2016-05-19 | 2016-05-20 | 2016-05-23 | 2016-05-24 | 2016-05-25 | 2016-05-26 | 2016-05-27 | Capacity | Availability
Chad | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 |  |  |  |  | 9.75 | 25%
Cindy | 6.5 | 6.5 | 6.5 | 6.5 |  | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 58.5 | 100%
Harry | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 |  | 29.25 | 50%
Jayne | 5.85 | 5.85 | 5.85 | 5.85 | 5.85 | 5.85 | 5.85 | 5.85 | 5.85 | 5.85 | 58.5 | 90%
John | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 65 | 100%
Ken | 5.525 | 5.525 |  | 5.525 | 5.525 | 5.525 | 5.525 |  | 5.525 | 5.525 | 44.2 | 85%
Mai | 2.6 | 2.6 | 2.6 |  |  | 2.6 | 2.6 | 2.6 |  |  | 15.6 | 40%
Shannon | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 16.25 | 25%
Sri | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 16.25 | 25%
Tran | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 |  | 23.4 | 40%
Srvc Mgr
Team Availability Avg % | [11 empty] | 58%
PMO Mtgs | 2.5 | 1.25 | 0.25 | 1.25 | 0.25 | 1.25 | 1.25 | 1.25 | 5.25 | 0.25 | 14.75
| 2016-05-26: Capatity | 336.7
| 2016-05-26: Normal Capacity | 650
| 2016-05-26: Capacity Shortfall | -313.3
| 2016-05-26: Available capacity % | 51.8%
| 2016-05-26: Loaded Work Day | 6.5
The grayed out fields are when someone was on vacation.
We base capacity on a 6.5 hour work day x 10 days in a sprint
Note on A16: Ken Shepard: Daily Standup - .25 (9) Sprint Retrospective - .50 CWDS Weekly - 1.00 (2) Sprint Review - 1.00 PMO Team mtg - 1.00 (2) Training Session - 1.00 (2) Sprint Planning - 1.00 Sprint Review Planning - 1.00

## Sprint 10
PMO Team
| Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Sprint | %
| 2016-05-30 | 2016-05-31 | 2016-06-01 | 2016-06-02 | 2016-06-03 | 2016-06-06 | 2016-06-07 | 2016-06-08 | 2016-06-09 | 2016-06-10 | Capacity | Availability
Chad |  | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 14.625 | 25%
Cindy |  | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 58.5 | 100%
Harry |  | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 29.25 | 50%
Jayne |  | 5.85 | 5.85 | 5.85 | 5.85 | 5.85 | 5.85 | 5.85 | 5.85 | 5.85 | 52.65 | 90%
John |  | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 58.5 | 100%
Ken |  |  |  | 5.525 | 5.525 | 5.525 | 5.525 | 5.525 | 5.525 | 5.525 | 38.675 | 85%
Mai |  | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 23.4 | 40%
Shannon |  |  |  | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 11.375 | 25%
Sri |  |  |  | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 11.375 | 25%
Tran |  | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 23.4 | 40%
Srvc Mgr
Team Availability Avg % | [11 empty] | 58%
PMO Mtgs | 0 | 0.25 | 0.25 | 1.25 | 1.25 | 1.25 | 1.75 | 1.25 | 2.25 | 0.25 | 9.75
| 2016-06-09: Capatity | 321.75
| 2016-06-09: Normal Capacity | 650
| 2016-06-09: Capacity Shortfall | -328.25
| 2016-06-09: Available capacity % | 49.5%
| 2016-06-09: Loaded Work Day | 6.5
The grayed out fields are when someone was on vacation.
We base capacity on a 6.5 hour work day x 10 days in a sprint
Note on A16: Ken Shepard: Daily Standup - .25 (9) Sprint Retrospective - .50 CWDS Weekly - 1.00 (2) Sprint Review - 1.00 PMO Team mtg - 1.00 (2) Training Session - 1.00 (2) Sprint Planning - 1.00 Sprint Review Planning - 1.00

## Sprint 11
Team Name
Enter team member names | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Sprint | %
| Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Capacity | Availability
Team Member 1 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 16.25 | 25%
Team Member 2 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 65 | 100%
Team Member 3 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | OOO | 6.5 | 58.5 | 100%
Team Member 4 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 3.25 | 32.5 | 50%
Team Member 5 | 5.85 | 5.85 | 5.85 | 5.85 | 5.85 | 5.85 | 5.85 | 5.85 | 5.85 | 5.85 | 58.5 | 90%
Team Member 6 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 65 | 100%
Team Member 7 | 4.875 | 4.875 | 4.875 | OOO | OOO | OOO | 4.875 | 4.875 | 4.875 | 4.875 | 34.125 | 75%
Team Member 8 | 2.6 | 2.6 | 2.6 | OOO | OOO | 2.6 | 2.6 | 2.6 | OOO | OOO | 15.6 | 40%
Team Member 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Team Member 10 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 1.625 | 16.25 | 25%
Scrum Master
Service Manager
Team Availability Avg % | [11 empty] | 60.5%
Team Meetings | 3.25 | 1.75 | 0.25 | 1.25 | 0.25 | 1.25 | 2.75 | 1.25 | 2.25 | 0.25 | 14.5
| Day 9: Capacity | 361.725
| Day 9: Normal Capacity | 650
| Day 9: Capacity Shortfall | -288.275
The grayed out fields are when someone is planned to be out of office. | Day 9: Available capacity % | 55.65%
We base capacity on a 6.5 hour work day x 10 days in a sprint
| Day 9: Loaded Work Day | 6.5
Team Meetings
Daily Standup - .25 (9)
Sprint Retrospective - 1.00
Sprint Review - 0.50
Team meeting - 1.00 (2)
Sprint Planning - 2.00
NOTE: There are formulas embedded in this spreadsheet. Following the instructions in the order listed below will activate and calculate the formulas present. INSTRUCTIONS: Step 1: In column M, enter the team member's allocation percentage. If they are not allocated to more than one team, enter 100% Step 2: In cell L24, the project has chosen a loaded work day of 6.50 hours. If that amount of time is not sufficient for your team, please discuss with your Service Manager. Step 3: Identify who will be out and when. In each day that a team member will be out of the office, enter OOO and highlight this in a color such as blue (shown above) so that it is visible to all. Step 4: For each day of the sprint, enter the number of hours the team will be meeting daily for the above listed meetings. This is more for information purposes to aid in adjusting the average loaded work day if needed. Step 5: Identify what the Available capacity % is in cell L22. Step 6: Identify the average velocity of the team (average is calculated from the last 3 sprints). Step 7: Multiply the average velocity by the percentage shown in cell L22. This is the amount of points that the team should attempt to take on during the sprint for which capacity has been calculated.
Note on M2: Karen Bruns: This field reflects the